## README
GRC Exception & Risk-Remediation Ticket Tracker
Fictional organization: Meridian Trust Financial (Canadian fintech) — for portfolio demonstration only
Purpose
This workbook tracks the full lifecycle of GRC exception tickets, policy deviations, and risk-acceptance
requests from intake through closure. It supports ISO/IEC 27001:2022 (Clause 6.1.3, Annex A.5.36,
A.8.9), NIST SP 800-53 Rev. 5 (CA-5 Plan of Action and Milestones, PM-4 Plan of Action Management),
and NIST SP 800-161 (supply chain risk exceptions).
How to use this workbook
1. Ticket Register — the master log. One row per ticket. Use the dropdown lists for standardized fields.
2. Dashboard — auto-calculated summary of open/overdue tickets, aging, and risk distribution.
3. Lookup Lists — controls the dropdown values used across the register (edit here to adjust options).
4. SLA Matrix — defines target turnaround time by residual risk rating; feeds the SLA Due Date formula.
Column logic (Ticket Register)
SLA Target Days is pulled automatically via VLOOKUP against the SLA Matrix, based on Residual Risk Rating.
SLA Due Date = Approval Date + SLA Target Days.
Days Open = Actual Closure Date minus Date Raised if closed, otherwise TODAY() minus Date Raised.
SLA Status flags Overdue, Due Soon (<=5 days), On Track, or Closed automatically.
Companion materials
A matching Word report, 'GRC Exception & Risk-Remediation Ticket Lifecycle Management Framework',
documents the 7-stage lifecycle, RACI, SLA model, KPIs, and control mapping in narrative form.

## Lookup Lists
Exception Type | Inherent/Residual Risk Rating | Approval Status | Ticket Status | Control Domain (ISO 27001:2022 Annex A / NIST 800-53 Family) | SLA Status (calculated, reference only)
Policy Exception | Critical | Pending Approval | Open | A.5 Access Control / AC | On Track
Risk Acceptance | High | Approved | Pending Approval | A.8.9 Configuration Management / CM | Due Soon
Standard Deviation | Medium | Approved with Conditions | In Remediation | A.8.16 Monitoring / AU | Overdue
Compensating Control | Low | Rejected | Pending Verification | A.5.19 Supplier Relationships / SA & SR (800-161) | Closed
Temporary Waiver |  | Escalated to Risk Committee | Reopened | A.8.24 Cryptography / SC
|  |  | Closed | A.8.8 Vulnerability Management / RA
|  |  | Rejected | A.5.29 ICT Continuity / CP
A.5.36 Compliance Review / CA

## SLA Matrix
Residual Risk Rating | SLA Target (Days to Closure) | Review/Re-certification Frequency | Escalation Trigger
Critical | 15 | Every 90 days | No remediation owner assigned within 2 business days
High | 30 | Every 180 days | 50% of SLA elapsed with no remediation plan on file
Medium | 60 | Annually | SLA breached by more than 10 days
Low | 90 | Annually | SLA breached by more than 20 days

## Ticket Register
Ticket ID | Date Raised | Requestor | Business Unit | System / Asset | Control Domain | Control Reference | Exception Type | Description | Inherent Risk Rating | Compensating Controls | Residual Risk Rating | Risk Owner | Approver | Approval Status | Approval Date | SLA Target (Days) | SLA Due Date | Remediation Owner | Remediation Plan Summary | Target Closure Date | Actual Closure Date | Ticket Status | Days Open | SLA Status | Next Review Date | Reopened Count | Closure Evidence Ref.
RXT-2026-001 | 2026-03-07 | D. Alaba (IT Ops) | Retail Banking Tech | Core Banking Gateway API | A.5.19 Supplier Relationships / SA & SR (800-161) | SR-3, ISO A.5.19-A.5.22 | Risk Acceptance | Third-party payment processor delayed SOC 2 Type II report beyond contractual deadline. | High | Monthly vendor call, interim attestation letter, enhanced transaction monitoring | Medium | M. Okonkwo (TPRM Lead) | Chief Risk Officer | Approved with Conditions | 2026-03-17 | 60 | 2026-05-16 | M. Okonkwo | Obtain SOC 2 Type II report; re-assess residual rating on receipt. | 2026-06-15 | 2026-06-17 | Closed | 102 | Closed | 2027-03-17 | 0 | EVID-2026-001-SOC2.pdf
RXT-2026-002 | 2026-04-01 | S. Choudhury (Infra) | Enterprise IT | Legacy File Server (WIN-FS02) | A.8.24 Cryptography / SC | SC-13, ISO A.8.24 | Standard Deviation | Server cannot support TLS 1.2 due to end-of-life OS; scheduled for decommission. | High | Network segmentation, restricted ACLs, decommission project underway | High | S. Choudhury | CISO | Approved with Conditions | 2026-04-08 | 30 | 2026-05-08 | S. Choudhury | Migrate file shares to hardened NAS; decommission WIN-FS02. | 2026-06-30 |  | In Remediation | 96 | Overdue | 2027-04-08 | 0
RXT-2026-003 | 2026-04-16 | A. Nwosu (App Dev) | Digital Banking | Mobile Banking App v4.2 | A.8.8 Vulnerability Management / RA | RA-5, ISO A.8.8 | Policy Exception | Medium-severity dependency vulnerability (outdated logging library) cannot be patched before next release window. | Medium | WAF rule added, dependency isolated from user input path | Low | A. Nwosu | App Security Lead | Approved | 2026-04-21 | 90 | 2026-07-20 | A. Nwosu | Upgrade library in Q3 release cycle; retest. | 2026-06-20 | 2026-06-21 | Closed | 66 | Closed | 2027-04-21 | 0 | EVID-2026-003-scan.pdf
RXT-2026-004 | 2026-05-06 | P. Osei (Access Mgmt) | Human Resources | HR Information System (Workday) | A.5 Access Control / AC | AC-6, ISO A.5.15-A.5.18 | Policy Exception | Contractor requires temporary elevated access beyond standard least-privilege baseline for payroll migration. | Medium | Time-boxed access (30 days), session logging enabled, manager sign-off | Low | P. Osei | HR Director | Approved | 2026-05-08 | 90 | 2026-08-06 | P. Osei | Revoke elevated access automatically at expiry; confirm via access review. | 2026-06-07 | 2026-06-07 | Closed | 32 | Closed | 2027-05-08 | 0 | EVID-2026-004-access.pdf
RXT-2026-005 | 2026-05-11 | T. Fagbenle (SOC) | Security Operations | SIEM Log Retention Policy | A.8.16 Monitoring / AU | AU-11, ISO A.8.16 | Standard Deviation | Cloud log retention configured for 180 days instead of policy-mandated 365 days due to storage cost cap. | Medium | Cold storage archive of logs beyond 180 days at reduced query capability | Medium | T. Fagbenle | CISO | Escalated to Risk Committee |  | 60 |  | T. Fagbenle | Present storage cost-benefit options to Risk Committee for final retention decision. | 2026-07-15 |  | Pending Approval | 56 | N/A |  | 0
RXT-2026-006 | 2026-05-18 | R. Adebayo (Vendor Mgmt) | Procurement | Cloud Backup Provider (NorthVault) | A.5.19 Supplier Relationships / SA & SR (800-161) | SR-6, ISO A.5.20 | Risk Acceptance | Vendor data processing agreement lacks explicit sub-processor notification clause required by internal standard. | Medium | Quarterly sub-processor list requested manually pending contract renewal | Medium | R. Adebayo | Chief Risk Officer | Approved with Conditions | 2026-05-26 | 60 | 2026-07-25 | R. Adebayo | Renegotiate DPA clause at next contract renewal (Q4 2026). | 2026-10-03 |  | In Remediation | 49 | On Track | 2027-05-26 | 0
RXT-2026-007 | 2026-05-26 | C. Mensah (BCP) | Business Continuity | Disaster Recovery Site (Ottawa DC) | A.5.29 ICT Continuity / CP | CP-7, ISO A.5.29-A.5.30 | Compensating Control | Annual DR failover test postponed due to data centre maintenance window conflict. | High | Tabletop exercise conducted in lieu; full failover rescheduled | Medium | C. Mensah | COO | Approved with Conditions | 2026-05-31 | 60 | 2026-07-30 | C. Mensah | Execute full failover test within 60 days of original schedule. | 2026-07-03 |  | Reopened | 41 | On Track | 2027-05-31 | 1
RXT-2026-008 | 2026-06-05 | K. Boateng (App Dev) | Digital Banking | Customer Portal Authentication | A.5 Access Control / AC | AC-7, IA-5, ISO A.8.5 | Policy Exception | MFA enrolment grace period extended for customers migrating from legacy authentication method. | Medium | Risk-based step-up authentication, fraud monitoring alerts enabled | Low | K. Boateng | CISO | Approved | 2026-06-07 | 90 | 2026-09-05 | K. Boateng | Complete MFA migration campaign; disable legacy path. | 2026-07-25 |  | In Remediation | 31 | On Track | 2027-06-07 | 0
RXT-2026-009 | 2026-06-10 | N. Eze (IT Ops) | Enterprise IT | Patch Management Baseline | A.8.8 Vulnerability Management / RA | SI-2, ISO A.8.8 | Standard Deviation | Critical OS patch deployment delayed on 12 servers pending change freeze during quarter-end processing. | High | Additional network monitoring and IDS tuning on affected hosts | High | N. Eze | CISO | Pending Approval |  | 30 |  | N. Eze | Deploy patches immediately after change freeze lifts. | 2026-07-12 |  | Open | 26 | N/A |  | 0
RXT-2026-010 | 2026-06-17 | F. Ibrahim (Data Governance) | Data & Analytics | Customer Data Warehouse | A.8.9 Configuration Management / CM | CM-3, ISO A.8.9 | Policy Exception | Emergency schema change deployed outside standard change-approval window to fix production reporting outage. | Medium | Post-implementation review scheduled; rollback plan documented | Low | F. Ibrahim | Change Advisory Board Chair | Approved | 2026-06-18 | 90 | 2026-09-16 | F. Ibrahim | Complete retrospective change review and update CAB record. | 2026-06-25 | 2026-06-26 | Closed | 9 | Closed | 2027-06-18 | 0 | EVID-2026-010-CAB.pdf
RXT-2026-011 | 2026-06-21 | J. Adeyemi (SOC) | Security Operations | Endpoint Detection & Response (EDR) | A.8.16 Monitoring / AU | SI-4, ISO A.8.16 | Temporary Waiver | EDR agent rollout delayed on 40 field-sales laptops due to VPN bandwidth constraints. | Medium | Interim host-based firewall hardening and manual log review | Medium | J. Adeyemi | CISO | Approved with Conditions | 2026-06-25 | 60 | 2026-08-24 | J. Adeyemi | Stagger EDR rollout in batches over next 3 weeks via off-peak sync. | 2026-07-20 |  | In Remediation | 15 | On Track | 2027-06-25 | 0
RXT-2026-012 | 2026-06-25 | L. Adesanya (Legal) | Legal & Compliance | Records Retention Schedule | A.5.36 Compliance Review / CA | CA-5, ISO A.5.36 | Risk Acceptance | Archived contract records retained 2 years beyond regulatory disposal date pending litigation hold review. | Low | Records isolated in restricted-access legal hold vault | Low | L. Adesanya | General Counsel | Approved | 2026-06-27 | 90 | 2026-09-25 | L. Adesanya | Release litigation hold and initiate disposal per schedule. | 2026-08-19 |  | Open | 11 | On Track | 2027-06-27 | 0
RXT-2026-013 | 2026-06-28 | B. Yusuf (Infra) | Enterprise IT | Firewall Rule Set (Perimeter) | A.5 Access Control / AC | AC-4, ISO A.8.20 | Standard Deviation | Broad outbound rule left temporarily open to support vendor data migration cutover. | High | Rule scoped to single vendor IP range with expiry date set | Medium | B. Yusuf | CISO | Approved with Conditions | 2026-06-29 | 60 | 2026-08-28 | B. Yusuf | Remove firewall rule immediately after migration cutover confirmed complete. | 2026-07-08 |  | Open | 8 | On Track | 2027-06-29 | 0
RXT-2026-014 | 2026-07-01 | H. Suleiman (App Dev) | Digital Banking | API Gateway Rate Limiting | A.8.24 Cryptography / SC | SC-5, ISO A.8.23 | Policy Exception | Rate-limiting thresholds temporarily relaxed to support partner onboarding load test. | Medium | Enhanced WAF monitoring and automatic rollback trigger configured | Low | H. Suleiman | App Security Lead | Pending Approval |  | 90 |  | H. Suleiman | Restore standard thresholds after load test window closes. | 2026-07-07 |  | Open | 5 | N/A |  | 0
RXT-2026-015 | 2026-07-03 | O. Balogun (TPRM) | Procurement | HR Payroll Outsourcing Vendor | A.5.19 Supplier Relationships / SA & SR (800-161) | SR-2, ISO A.5.21 | Risk Acceptance | Vendor annual penetration test report overdue by 3 weeks; renewal contract under negotiation. | Medium | Interim vulnerability self-attestation obtained from vendor | Medium | O. Balogun | Chief Risk Officer | Pending Approval |  | 60 |  | O. Balogun | Obtain overdue pen-test report and reassess before contract renewal signature. | 2026-07-30 |  | Open | 3 | N/A |  | 0
Formulas:
SLA Due Date = IF([Approval Date]="","",IF([SLA Target (Days)]="","",[Approval Date]+[SLA Target (Days)]))
Days Open = IF([Actual Closure Date]<>"",[Actual Closure Date]-[Date Raised],TODAY()-[Date Raised])
SLA Status = IF([Ticket Status]="Closed","Closed",IF([SLA Due Date]="","N/A",IF(TODAY()>[SLA Due Date],"Overdue",IF([SLA Due Date]-TODAY()<=5,"Due Soon","On Track"))))
Next Review Date = IF([Approval Date]="","",[Approval Date]+365)

## Dashboard
GRC Exception Ticket Dashboard
Meridian Trust Financial — live summary (auto-calculated from Ticket Register)
Tickets by Status |  | Open Tickets by Residual Risk
Open | 5 | Critical | 0
Pending Approval | 1 | High | 2
In Remediation | 4 | Medium | 6
Pending Verification | 0 | Low | 3
Reopened | 1
Closed | 4
Rejected | 0
Total | 15
SLA Health (open tickets only) |  | Aging Metrics
Overdue | 1 | Average days open (all tickets) | 36.7
Due Soon (<=5 days) | 0 | Longest open ticket (days) | 102
On Track | 6 | Tickets reopened (total) | 1